## BLUE
No | PD Version | Site ID | ATC SITE ID | Site Name | City/Town | VENDOR | NEW Vendors | SIM Card | Serial Number | Status | Comment | ATC 1 Supervisor | ATC 2 Supervisor | Handlers | Responsible | ETA | Picked from Site? | Delivered to Ben | Returned to Site? | ETA for re-installation | Comment
14 | Version 5 | ETO/UG/20009/JIN | 608101 | Jinja BSC(Magwa) | Jinja | Netis |  | 771467878 | 8.9256e+19 | WORKING |  | Emmanuel Kafuko | Samuel Naseke | Emmanuel Kafuko & Samuel Naseke | Samuel Naseke | 2020-06-26 | Yes | Yes | Yes |  |  | Samuel Naseke | 772718248
24 | Version 5 | ETO/UG/40004/ARU | 608614 | Arua National Water | Arua | I-Engineering |  | 771483320 | 8.9256e+19 | FAULTY | Replaced with new Unit from ATC Red | Muhamud Muhumuza | Thomasi Seruyange | Muhamud Muhumuza & Thomasi Seruyange | Thomasi Seruyange | 2020-06-26 | Yes | Yes | Yes
28 | Version 5 | ETO/UG/20074/MBL | 608028 | Bugiri HQ | Bugiri | Netis |  | 757723885 | 8.9256e+19 | WORKING |  | Emmanuel Kafuko | Jude Musana | Emmanuel Kafuko & Jude Musana | George Waako | 2020-06-26 | Yes | Yes | No |  | Faulty
9 | Version 5 | ETO/UG/30005/FPL | 609056 | Fort portal | Fort Portal | Camusat |  | 757723576 | 8.9256e+19 | WORKING |  | Robert Otim | Patrick Kinyera | Robert Otim & Patrick Kinyera | Patrick Kinyera | 2020-06-27 | Yes | Yes | Yes |  |  | Christopher Alituha | 771003451
8 | Version 5 | ETO/UG/10036/KMP | 607119 | Fourth Street | Kampala | Netis |  | 757723555 | 8.9256e+19 | WORKING |  | George Waako | M Patrick Kalibbala | George Waako & M Patrick Kalibbala | M Patrick Kalibbala | 2020-06-26 | Yes | Yes | Yes |  |  | M Patrick Kalibbala | 772718246
15 | Version 5 | ETO/UG/40019/GUL | 608554 | Gulu Town BSC | Gulu | I-Engineering |  | 770626314 | 8.9256e+19 | WORKING |  | Muhamud Muhumuza | Stephen Rwabweogo | Muhamud Muhumuza & Stephen Rwabweogo | Stephen Rwabwogo | 2020-06-27 | Yes | Yes | Yes |  |  | Patrick Kinyera | 776317068
20 | Version 5 | ETO/UG/30162/HOI | 609067 | Hoima | Hoima | Camusat |  | 770622709 | 8.9256e+19 | WORKING | Replaced with that of Wakiso | Muhamud Muhumuza | Christopher Alituha | Muhamud Muhumuza & Christopher Alituha | George Waako | 2020-06-26 | Yes | Yes | No |  | Faulty
18 | Version 5 | ETOU/UG/30034/MBR | 609090 | Kabale 2 | Kabale | Camusat |  | 757723508 | 8.9256e+19 | WORKING |  | Robert Otim | Christopher Alituha | Robert Otim & Christopher Alituha | Robert Otim | 2020-06-27 | Yes | Yes | No |  | Pending installation by Robert Otim
3 | Version 5 | ETOU/UG/10034/KMP | 607145 | Kabira club | kampala | I-Engineering |  | 757723820 | 8.9256e+19 | WORKING | Unit was taken to Kireka Kamili | Emmy Ndyamureeba | M Patrick Kalibbala | Emmy Ndyamureeba & M Patrick Kalibbala |  | Not present |  |  |  |  | At St. Andrew | George Waako | 759990805
1 | Version 5 | ETO/UG/10056/KMP | 607146 | Kabowa | Kampala | Camusat |  | 771485747 | 8.9256e+19 | WORKING |  | George Waako | M Patrick Kalibbala | George Waako & M Patrick Kalibbala | M Patrick Kalibbala | 2020-06-26 | Yes | Yes | Yes
16 | Version 5 | ETO/UG/30025/MBR | 609114 | Kakyeka | Mbarara | Camusat |  | 757723840 | 8.9256e+19 | WORKING |  | Robert Otim | Christopher Alituha | Robert Otim & Christopher Alituha | M Patrick Kalibbala | 2020-06-27 | Yes | Yes | Yes |  |  | Godfrey Mugisha | 772718241
2 | Version 5 | ETO/UG/10153/KMP | 607207 | Katakala | Mityana | Camusat |  | 757723578 | 8.9256e+19 | WORKING |  | Emmy Ndyamureeba | Christopher Alituha | Emmy Ndyamureeba & Christopher Alituha | Patrick Kinyera | 2020-06-27 | Yes | Yes | Yes |  |  | Contacts
7 | Version 5 | ETO/UG/10097/KMP | 607265 | Kireka Kamuli | Kampala | Netis |  | 757723548 | 8.9256e+19 | WORKING |  | George Waako | M Patrick Kalibbala | George Waako & M Patrick Kalibbala | M Patrick Kalibbala | 2020-06-26 | Yes | Yes | Yes |  |  | Emmanuel Kafuko | 752600673
25 | Version 5 | ETO/UG/40046/GUL | 608573 | Kitgum | Kitgum | I-Engineering |  | 771480513 | 8.9256e+19 | FAULTY |  | Muhamud Muhumuza | Stephen Rwabweogo | Muhamud Muhumuza & Stephen Rwabweogo | Stephen Rwabwogo | Not present |  |  |  |  | Missing
12 | Version 5 | ETOU/UG/40026/GUL | 608590 | Lira | Lira | I-Engineering |  | 757723651 | 8.9256e+19 | WORKING |  | Muhamud Muhumuza | Stephen Rwabweogo | Muhamud Muhumuza & Stephen Rwabweogo | Stephen Rwabwogo | 2020-06-27 | Yes | Yes | Yes |  |  | Thomasi Seruyange | 780140633
13 | Version 5 | ETOU/UG/20057/MOR | 608163 | Lothaa | Napak | Netis |  | 771469184 | 8.9256e+19 | WORKING |  | Emmanuel Kafuko | Jude Musana | Emmanuel Kafuko & Jude Musana | Jude Musana | 2020-06-27 | Yes | Yes | No |  | Faulty | Jude Musana | 772718244
5 | Version 5 | ETO/UG/10117/KMP | 607385 | Luwero | Luwero | I-Engineering |  | 757723588 | 8.9256e+19 | WORKING | Replaced with a new from ATC Red | Emmy Ndyamureeba | Sam Mwambu | Emmy Ndyamureeba & Sam Mwambu | Sam Mwambu | 2020-06-26 | Yes | Yes | Yes |  |  | Robert Otim | 792222404
29 | Version 5 | ETO/UG/20119/MBL | 608185 | Malaba Fiber | Tororo | Netis |  | 771495784 | 8.9256e+19 | WORKING |  | Emmanuel Kafuko | Jude Musana | Emmanuel Kafuko & Jude Musana | Jude Musana | 2020-06-27 | Yes | Yes | Yes
10 | Version 5 | ETO/UG/30050/MSK | 607424 | Masaka Kizungu | Masaka | Camusat |  | 757723505 | 8.9256e+19 | WORKING |  | Robert Otim | Christopher Alituha | Robert Otim & Christopher Alituha | M Patrick Kalibbala | 2020-06-27 | Yes | Yes | Yes |  |  | Sam Mwambu | 772718227
22 | Version 5 | ETO/UG/30058/MAS | 609228 | Masindi BSC | Masindi | I-Engineering |  | 770624711 | 8.9256e+19 | WORKING |  | Muhamud Muhumuza | Godfrey Mugisha | Muhamud Muhumuza & Godfrey Mugisha | Godfrey Mugisha | 2020-06-28 | Yes | Yes | Yes
27 | Version 5 | ETO/UG/20026/MBL | 608197 | Mbale St. Andrews | Mbale | Netis |  | 771495819 | 8.9256e+19 | FAULTY | Unit from Kireka was taken to Mbale st | Emmanuel Kafuko | Jude Musana | Emmanuel Kafuko & Jude Musana | Jude Musana | 2020-06-28 | Yes | Yes | Yes
17 | Version 5 | ETO/UG/30189/MBR | 609235 | Mbarara BSC | Mbarara | Camusat |  | 757723518 | 8.9256e+19 | WORKING |  | Robert Otim | Christopher Alituha | Robert Otim & Christopher Alituha | M Patrick Kalibbala | 2020-06-27 | Yes | Yes | Yes
11 | Version 5 | ETO/UG/30034/MBR | 609236 | Mbarara BSC(Kamukuzi) | Mbarara | Camusat |  | 757723760 | 8.9256e+19 | WORKING |  | Robert Otim | Christopher Alituha | Robert Otim & Christopher Alituha | M Patrick Kalibbala | 2020-06-27 | Yes | Yes | Yes |  |  | Stephen Rwabwogo | 771014820
21 | Version 5 | ETO/UG/30057/FPL | 609249 | Mubende Hill | Mubende | Camusat |  | 757723727 | 8.9256e+19 | FAULTY | New unit to be deployed today | Emmy Ndyamureeba | Godfrey Mugisha | Emmy Ndyamureeba & Patrick Kinyera | Patrick Kinyera | 2020-06-27 | Yes | Yes | Yes
30 | Version 5 | ETO/UG/10225/KMP | 607465 | Mukono Hill | Mukono | Netis |  | 757723862 | 8.9256e+19 | WORKING |  | George Waako | Samuel Naseke | George Waako & Samuel Naseke | Samuel Naseke | 2020-06-26 | Yes | Yes | Yes
23 | Version 5 | ETO/UG/10129/KMP | 607516 | Nakasongola | Nakasongola | I-Engineering |  | 771476935 | 8.9256e+19 | WORKING |  | Muhamud Muhumuza | Sam Mwambu | Muhamud Muhumuza & Sam Mwambu | Godfrey Mugisha | 2020-06-27 | Yes | Yes | Yes
6 | Version 5 | ETOU/UG/10119/KMP | 607582 | Nsambya | Nsambya | Netis |  | 757723829 | 8.9256e+19 | WORKING |  | George Waako | Christopher Alituha | George Waako & Christopher Alituha | George Waako | 2020-06-26 | Yes | Yes |  |  | Faulty | Muhamud Muhumuza | 779044015
19 | Version 5 | ETO/UG/30060/MBR | 609280 | Ntungamo | Ntungamo | Camusat |  | 757723704 | 8.9256e+19 | WORKING |  | Robert Otim | Christopher Alituha | Robert Otim & Christopher Alituha | Robert Otim | 2020-06-27 | Yes | Yes | No |  | Pending installation by Robert Otim
26 | Version 5 | ETO/UG/20039/MBL | 608271 | Taqwa Mosque | Soroti | Netis |  | 771495865 | 8.9256e+19 | WORKING |  | Emmanuel Kafuko | Jude Musana | Emmanuel Kafuko & Jude Musana | Jude Musana | 2020-06-27 | Yes | Yes | Yes
4 | Version 5 | ETO/UG/10193/KMP | 607651 | Wakiso | Wakiso | Camusat |  | 757723830 | 8.9256e+19 | WORKING | Replaced With new from ATC Red | Emmy Ndyamureeba | M Patrick Kalibbala | Emmy Ndyamureeba & M Patrick Kalibbala | Iengineering | 2020-06-26 | Yes | Yes | No |  | Pending installation by I-Engineering | Emmy Ndyamureeba | 759990801

## RED SITES
No | Area / Vendor | PD Version | Deployment Status | Site ID | Latitude | Longitude | MAC Address | Serial Number | SIM Card | Serial Number | Received by | Date | REMARKS
1 | Tororo | Version 5 | Deployed | 605091 | 0.71181 | 34.1843 | 00-08-B5-13-0B-C1 | ATC-UG-PD-025 | 771000145 | 01034462788 | Mateeka Abdallah | 2015-10-28
3 | Soroti | Version 5 | Deployed | 605068 | 1.7117 | 33.6148 | 00-08-B5-13-0B-BC | ATC-UG-PD-034 | 783909532 | 00983162472 | Francis Serwanja | 2016-02-17
8 | Rukungiri | Version 5 | Deployed | 605180 | -0.79116 | 29.9253 | 00-08-B5-13-0C-07 | ATC-UG-KC-004 | 788160046 | 0108975799 |  |  | Missing
9 | Rugarama | Version 4 | Deployed | 605220 | -1.2387 | 29.9858 | FF-FF-FF-FF-FF-FF | ATC-UG-PD-006 | 783909655 | 00983162548 | Patrick Kalibala | 2015-08-18
10 | Rakai | Version 5 | Deployed | 605151 | -0.70526 | 31.4084 | 00-08-B5-13-0C-83 | ATC-UG-KC-010 | 788159991 | 0108975791 | Mateeka Abdallah | 2016-09-05
12 | Ntungamo | Version 5 | Deployed | 605178 | -0.86836 | 30.2364 | 00-08-B5-13-0C-09 | ATC-UG-KC-035 | 783909685 | 00983162571
14 | Nebbi Town | Version 5 | Deployed | 605886 | 2.48 | 31.0891 | 00-08-B5-13-0C-04 | ATC-UG-KC-011 | 788160058 | 0108975803 | Mateeka Abdallah | 2016-09-05
15 | Mubende | Version 5 | Deployed | 605122 | 0.5653 | 31.3814 | 00-08-B5-13-0B-BF | ATC-UG-PD-013 | 783909688 | 00983162597 | Patrick Kinyera | 2017-09-30
16 | MTN BAT | Version 5 | Deployed | 605064 | 0.31948 | 32.5979 | 00-08-B5-13-0B-C0 | ATC-UG-PD-035 | 771405049 | 01032481814 | Ronald Higenyi | 2016-05-11
17 | Mpigi Town | Version 5 | Deployed | 605254 | 0.22318 | 32.3237 | 00-08-B5-13-0C-7A | ATC-UG-KC-027 | 788160103 | 0108975807 | Mateeka Abdallah | 2016-09-05
18 | Mityana Market | Version 5 | Deployed | 605301 | 0.40136 | 32.0459 | 00-08-B5-13-0C-26 | ATC-UG-KC-031 | 788160057 | 0108975802 | Mateeka Abdallah | 2016-09-05
19 | Mbuya Switch | Version 5 | Deployed | 605206 | 0.32048 | 32.6247 | 00-08-B5-13-0B-CA | ATC-UG-PD-028 | 771405200 | 01033723230 | Ronald Higenyi | 2016-05-11
20 | Mbarara Golf | Version 5 | Deployed | 605021 | -0.61077 | 30.6584 | 00-08-B5-13-0B-B9 | ATC-UG-PD-012 | 771000158 | 01034467357 | Mateeka Abdallah | 2015-09-23
21 | Mbale SS | Version 4 | Deployed | 605247 | 1.081 | 34.172 | FF-FF-FF-FF-FF-FF | ATC-UG-PD-003 | 783909654 | 00983162530 | Jude Musana | 2015-09-03
22 | Masindi | Version 4 | Deployed | 605790 | 1.6822 | 31.7184 | FF-FF-FF-FF-FF-FF | ATC-UG-PD-010 | 772718183 | 01032434243 | Mateeka Abdallah | 2015-09-23
23 | Masaka Sports | Version 5 | Deployed | 605020 | -0.33723 | 31.7341 | 00-08-B5-13-0B-A8 | ATC-UG-PD-030 | 771000170 | 01034466227 | Mateeka Abdallah | 2015-09-23
24 | Galooli Uganda | Version 5 | Deployed | 605060 | 0.00595 | 32.0147 | FF-FF-FF-FF-FF-FF | ATC-UG-PD-029 | 771405047 | 01031375108 | Mateeka Abdallah | 2016-02-11
25 | Lyantonde | Version 5 | Deployed | 605367 | -0.44376 | 31.0695 | 00-08-B5-13-0B-AE | ATC-UG-KC-038 | 783909719 | 00983161276 | Mateeka Abdallah | 2016-05-09
26 | Luwero | Version 5 | Deployed | 605082 | 0.84119 | 32.4929 | 00-08-B5-13-0D-B6 | ATC-UG-NK-014 | 771405156 | 01032384067
27 | Lira | Version 5 | Deployed | 605121 | 2.2355 | 32.9042 | 00-08-B5-13-0B-C3 | ATC-UG-PD-014 | 771003226 | 01034453340 | Stephen Rwabogo | 2015-10-01
28 | Kyegegwa | Version 5 | Deployed | 605409 | 0.47497 | 31.0696 | 00-08-B5-13-0B-6B | ATC-UG-KC-006 | 788160115 | 0108975809 | Mateeka Abdallah | 2016-09-05
29 | Kotido | Version 5 | Deployed | 605338 | 3.011 | 34.1165 | 00-08-B5-13-0C-6A | ATC-UG-KC-041 | 788160126 | 0108975811 | Mateeka Abdallah | 2016-09-05 | Vandalised/Missing
30 | Kitgum | Version 5 | Deployed | 605316 | 3.2899 | 32.8792 | 00-08-B5-13-0B-6E | ATC-UG-PD-024 | 771405217 | 01032149304 |  |  | Missing
31 | Kisoro | Version 5 | Deployed | 605110 | -1.2852 | 29.6916 | 00-08-B5-13-0B-BD | ATC-UG-PD-031 | 771405233 | 01031610520 | Mateeka Abdallah | 2016-02-11
32 | Kigumba | Version 5 | Deployed | 605842 | 1.8085 | 32.0088 | 00-08-B5-13-0B-EB | ATC-UG-KC-028 | 788159976 | 0108975790 | Mateeka Abdallah | 2016-09-05
33 | Kasese | Version 5 | Deployed | 605102 | 0.18568 | 30.0695 | 00-08-B5-13-0B-D4 | ATC-UG-PD-017 | 771405161 | 01032384372
34 | Karuma | Version 5 | Deployed | 605388 | 2.2405 | 32.2556 | FF-FF-FF-FF-FF-FF | ATC-UG-PD-019 | 771405165 | 01033709999 | Mateeka Abdallah | 2015-10-07
35 | Kamuli | Version 5 | Deployed | 605100 | 0.94409 | 33.1212 | 00-08-B5-13-0D-B8 | ATC-UG-NK-016 | 783909470 | 0120875716
36 | Kalangala | Version 5 | Deployed | 605160 | -0.32462 | 32.2852 | 00-08-B5-13-0B-B7 | ATC-UG-PD-033 | 783909614 | 00983162514 | Mateeka Abdallah | 2016-02-11
40 | Ibanda | Version 5 | Deployed | 605213 | -0.21876 | 30.504 | 00-08-B5-13-0C-28 | ATC-UG-KC-001 | 771405111 | 01033717596 | Mateeka Abdallah | 2016-05-09
41 | Hoima | Version 4 | Deployed | 605135 | 1.4434 | 31.3699 | 00-08-B5-13-0B-4D | ATC-UG-PD-001 | 771405181 | 01034463901 | Mugisha Godfrey | 2016-02-05
42 | Gulu | Version 5 | Deployed | 605124 | 2.7689 | 32.3021 | 00-08-B5-13-0D-A1 | ATC-UG-NK-012 | 788160066 | 0108975804
45 | Fortportal | Version 4 | Deployed | 605101 | 0.64693 | 30.2737 | FF-FF-FF-FF-FF-FF | ATC-UG-PD-008 | 783909687 | 00983162589 | Ndaula Kenneth | 2015-09-10
46 | Entebbe | Version 5 | Deployed | 605012 | 0.052892 | 32.4657 | 00-08-B5-13-0C-70 | ATC-UG-KC-003 | 788160079 | 0108975805
47 | Colline Hotel | Version 5 | Deployed | 605185 | 0.35804 | 32.7545 | 00-08-B5-13-0B-69 | ATC-UG-KC-037 | 783909702 | 00983162605 | Mateeka Abdallah | 2016-09-05
49 | Buvuma Island | Version 5 | Deployed | 605446 | 0.15887 | 33.2841 | 00-08-B5-13-0C-2F | ATC-UG-KC-017 | 788160098 | 0108975806 | Mateeka Abdallah | 2016-09-05
50 | Bushenyi | Version 5 | Deployed | 605072 | -0.5422 | 30.1868 | 00-08-B5-13-0C-4C | ATC-UG-KC-043 | 788160109 | 0108975808 | Mateeka Abdallah | 2016-09-05
51 | ATC Warehouse | Version 5 | Deployed | 608887 | 0.3413 | 32.6187 | 00-08-B5-13-0D-82 | ATC-UG-NK-017 | 783909558 | 0120875715
53 | Arua | Version 4 | Deployed | 605134 | 3.0107 | 30.9168 | 00-08-B5-13-0B-17 | ATC-UG-PD-009 | 772239198 | 01033107251 | Mateeka Abdallah | 2015-09-23
57 | Kiboga | Version 5 | Deployed | 605277 | 0.91595 | 31.7735 | 00-08-B5-13-0B-A0 | ATC-UG-PD-011 | 783909663 | 00983162555 | Mateeka Abdallah | 2016-05-04
58 | Adjuman | Version 5 | Deployed | 605284 | 3.3756 | 31.7845 | 00-08-B5-13-0B-B1 | ATC-UG-PD-032 | 771405273 | 01034469601 | Mateeka Abdallah | 2016-05-04
Note on B33: Author: From the spares

## Red-Blue
ATC SITE ID | Site Name | City/Town | NEW Vendors | SIM Card | Serial Number | Latitude | Longitude | To be relocated | Proposed New location ID | Proposed New location Site Name | New Location Latitude | New Location Longitude
608101 | Jinja BSC(Magwa) | Jinja | Netis | 771467878 | 8.9256e+19 | 0.452 | 33.2135
608614 | Arua National Water | Arua | I-Engineering | 771483320 | 8.9256e+19 | 3.011 | 30.9168
609056 | Fort portal | Fort Portal | Camusat | 757723576 | 8.9256e+19 | 0.6472 | 30.2728
607119 | Fourth Street | Kampala | Netis | 757723555 | 8.9256e+19 | 0.3244 | 32.6052 | Yes | 608034 | Kayunga | 0.70353 | 33.0256
608554 | Gulu Town BSC | Gulu | I-Engineering | 770626314 | 8.9256e+19 | 2.7681 | 32.302
607146 | Kabowa | Kampala | Camusat | 771485747 | 8.9256e+19 | 0.2844 | 32.5563
609114 | Kakyeka | Mbarara | Camusat | 757723840 | 8.9256e+19 | -0.597 | 30.6482 | Yes | 607393 | Lwemiyaga | 0.09005 | 31.0935
607207 | Katakala | Mityana | Camusat | 757723578 | 8.9256e+19 | 0.4042 | 32.0191 | Yes | 605778 | Koome | -0.10002 | 32.7356
607265 | Kireka Kamuli | Kampala | Netis | 757723548 | 8.9256e+19 | 0.3516 | 32.6475
608590 | Lira | Lira | I-Engineering | 757723651 | 8.9256e+19 | 2.2378 | 32.8942 | Yes | 605432 | Kalongo | 3.0427 | 33.3656
607385 | Luwero | Luwero | Netis | 757723588 | 8.9256e+19 | 0.8452 | 32.4904 | Yes | 607630 | Semuto | 0.626 | 32.3354
608185 | Malaba Fiber | Tororo | Netis | 771495784 | 8.9256e+19 | 0.61375 | 34.1836 | Yes | 608217 | Nakapiripirit | 1.8776 | 34.7259
607424 | Masaka Kizungu | Masaka | Camusat | 757723505 | 8.9256e+19 | -0.3375 | 31.7343
609228 | Masindi BSC | Masindi | Camusat | 770624711 | 8.9256e+19 | 1.6816 | 31.7226 | Yes | 609208 | Kyankwanzi | 0.3559 | 31.6041
608197 | Mbale St. Andrews | Mbale | Netis | 771495819 | 8.9256e+19 | 1.0739 | 34.1748
609235 | Mbarara BSC | Mbarara | Camusat | 757723518 | 8.9256e+19 | -0.60224 | 30.6636
609236 | Mbarara BSC(Kamukuzi) | Mbarara | Camusat | 757723760 | 8.9256e+19 | -0.6091 | 30.6417 | Yes | 609097 | Kagadi | 0.94634 | 30.8063
609249 | Mubende Hill | Mubende | Camusat | 757723727 | 8.9256e+19 | 0.5658 | 31.3816 | Yes | 605479 | Endinzi | -0.87206 | 31.0888
607465 | Mukono Hill | Mukono | Netis | 757723862 | 8.9256e+19 | 0.35158 | 32.743 | Yes | 608050 | Busembatia | 0.77533 | 33.6251
607516 | Nakasongola | Nakasongola | I-Engineering | 771476935 | 8.9256e+19 | 1.3231 | 32.4767
608271 | Taqwa Mosque | Soroti | Netis | 771495865 | 8.9256e+19 | 1.7163 | 33.6188 | Yes | 605339 | Moroto | 2.5284 | 34.6453
605091 | Tororo | Tororo | Netis | 771000145 | 01034462788 | 0.71181 | 34.1843
605068 | Soroti | Soroti | Netis | 783909532 | 00983162472 | 1.7117 | 33.6148
605180 | Rukungiri | Rukungiri | Camusat | 788160046 | 0108975799 | -0.79116 | 29.9253
605220 | Rugarama | Kabale | Camusat | 783909655 | 00983162548 | -1.2387 | 29.9858
605151 | Rakai | Rakai | Camusat | 788159991 | 0108975791 | -0.70526 | 31.4084
605178 | Ntungamo | Ntungamo | Camusat | 783909685 | 00983162571 | -0.86836 | 30.2364
605886 | Nebbi Town | Nebbi | I-Engineering | 788160058 | 0108975803 | 2.48 | 31.0891
605122 | Mubende | Mubende | Camusat | 783909688 | 00983162597 | 0.5653 | 31.3814
605064 | MTN BAT | Kampala | Netis | 771405049 | 01032481814 | 0.31948 | 32.5979
605254 | Mpigi Town | Mpigi | Camusat | 788160103 | 0108975807 | 0.22318 | 32.3237
605301 | Mityana Market | Mityana | Camusat | 788160057 | 0108975802 | 0.40136 | 32.0459
605206 | Mbuya Switch | Kampala | Netis | 771405200 | 01033723230 | 0.32048 | 32.6247
605021 | Mbarara Golf | Mbarara | Camusat | 771000158 | 01034467357 | -0.61077 | 30.6584
605247 | Mbale SS | Mbale | Netis | 783909654 | 00983162530 | 1.081 | 34.172
605790 | Masindi | Masindi | Camusat | 772718183 | 01032434243 | 1.6822 | 31.7184
605020 | Masaka Sports | Masaka | Camusat | 771000170 | 01034466227 | -0.33723 | 31.7341
605060 | Galooli Uganda | Mpigi | Camusat | 771405047 | 01031375108 | 0.00595 | 32.0147
605367 | Lyantonde | Kiruhura | Camusat | 783909719 | 00983161276 | -0.44376 | 31.0695
605082 | Luwero | Luwero | Netis | 771405156 | 01032384067 | 0.84119 | 32.4929
605121 | Lira | Lira | I-Engineering | 771003226 | 01034453340 | 2.2355 | 32.9042
605409 | Kyegegwa | Kyegegwa | Camusat | 788160115 | 0108975809 | 0.47497 | 31.0696
605338 | Kotido | Kotido | Netis | 788160126 | 0108975811 | 3.011 | 34.1165
605316 | Kitgum | Kitgum | I-Engineering | 771405217 | 01032149304 | 3.2899 | 32.8792
605110 | Kisoro | Kisoro | Camusat | 771405233 | 01031610520 | -1.2852 | 29.6916
605842 | Kigumba | Masindi | I-Engineering | 788159976 | 0108975790 | 1.8085 | 32.0088
605102 | Kasese | Kasese | Camusat | 771405161 | 01032384372 | 0.18568 | 30.0695
605388 | Karuma | Kiryandongo | I-Engineering | 771405165 | 01033709999 | 2.2405 | 32.2556
605100 | Kamuli | Kamuli | Netis | 783909470 | 0120875716 | 0.94409 | 33.1212
605160 | Kalangala | Kalangala | Camusat | 783909614 | 00983162514 | -0.32462 | 32.2852
605213 | Ibanda | Ibanda | Camusat | 771405111 | 01033717596 | -0.21876 | 30.504
605135 | Hoima | Hoima | Camusat | 771405181 | 01034463901 | 1.4434 | 31.3699
605124 | Gulu | Gulu | I-Engineering | 788160066 | 0108975804 | 2.7689 | 32.3021
605101 | Fortportal | Kabarole | Camusat | 783909687 | 00983162589 | 0.64693 | 30.2737
605012 | Entebbe | Wakiso | Camusat | 788160079 | 0108975805 | 0.052892 | 32.4657
605185 | Colline Hotel | Mukono | Netis | 783909702 | 00983162605 | 0.35804 | 32.7545
605446 | Buvuma Island | Buvuma | Netis | 788160098 | 0108975806 | 0.15887 | 33.2841
605072 | Bushenyi | Bushenyi | Camusat | 788160109 | 0108975808 | -0.5422 | 30.1868
608887 | ATC Warehouse | #N/A | #N/A | 783909558 | 0120875715 | 0.3413 | 32.6187
605134 | Arua | Arua | I-Engineering | 772239198 | 01033107251 | 3.0107 | 30.9168
605277 | Kiboga | Kiboga | Camusat | 783909663 | 00983162555 | 0.91595 | 31.7735
605284 | Adjuman | Adjumani | I-Engineering | 771405273 | 01034469601 | 3.3756 | 31.7845
Note on B54: Author: From the spares

## PDs In Close Proximity (hidden)
ATC SITE ID | Site Name | City/Town | NEW Vendors | SIM Card | Serial Number | Latitude | Longitude | To be recovered | Proposed New location ID | Proposed New location Site Name | New Location Latitude | New Location Longitude
608614 | Arua National Water | Arua | I-Engineering | 771483320 | 8.9256e+19 | 3.011 | 30.9168
605134 | Arua | Arua | I-Engineering | 772239198 | 01033107251 | 3.0107 | 30.9168
609056 | Fort portal | Fort Portal | Camusat | 757723576 | 8.9256e+19 | 0.6472 | 30.2728
607119 | Fourth Street | Kampala | Netis | 757723555 | 8.9256e+19 | 0.3244 | 32.6052 | Yes | 608034 | Kayunga | 0.70353 | 33.0256
608554 | Gulu Town BSC | Gulu | I-Engineering | 770626314 | 8.9256e+19 | 2.7681 | 32.302
609114 | Kakyeka | Mbarara | Camusat | 757723840 | 8.9256e+19 | -0.597 | 30.6482 | Yes | 607393 | Lwemiyaga | 0.09005 | 31.0935
607207 | Katakala | Mityana | Camusat | 757723578 | 8.9256e+19 | 0.4042 | 32.0191 | Yes | 605778 | Koome | -0.10002 | 32.7356
608590 | Lira | Lira | I-Engineering | 757723651 | 8.9256e+19 | 2.2378 | 32.8942 | Yes | 605432 | Kalongo | 3.0427 | 33.3656
607385 | Luwero | Luwero | Netis | 757723588 | 8.9256e+19 | 0.8452 | 32.4904 | Yes | 607630 | Semuto | 0.626 | 32.3354
608185 | Malaba Fiber | Tororo | Netis | 771495784 | 8.9256e+19 | 0.61375 | 34.1836 | Yes | 605506 | Amudat | 1.4675 | 34.8199
607424 | Masaka Kizungu | Masaka | Camusat | 757723505 | 8.9256e+19 | -0.3375 | 31.7343
609228 | Masindi BSC | Masindi | Camusat | 770624711 | 8.9256e+19 | 1.6816 | 31.7226 | Yes | 609208 | Kyankwanzi | 0.3559 | 31.6041
608197 | Mbale St. Andrews | Mbale | Netis | 771495819 | 8.9256e+19 | 1.0739 | 34.1748
609235 | Mbarara BSC | Mbarara | Camusat | 757723518 | 8.9256e+19 | -0.60224 | 30.6636
609236 | Mbarara BSC(Kamukuzi) | Mbarara | Camusat | 757723760 | 8.9256e+19 | -0.6091 | 30.6417 | Yes | 609097 | Kagadi | 0.94634 | 30.8063
609249 | Mubende Hill | Mubende | Camusat | 757723727 | 8.9256e+19 | 0.5658 | 31.3816 | Yes | 605479 | Endinzi | -0.87206 | 31.0888
607465 | Mukono Hill | Mukono | Netis | 757723862 | 8.9256e+19 | 0.35158 | 32.743 | Yes | 608050 | Busembatia | 0.77533 | 33.6251
608271 | Taqwa Mosque | Soroti | Netis | 771495865 | 8.9256e+19 | 1.7163 | 33.6188 | Yes | 605339 | Moroto | 2.5284 | 34.6453
605091 | Tororo | Tororo | Netis | 771000145 | 01034462788 | 0.71181 | 34.1843
605068 | Soroti | Soroti | Netis | 783909532 | 00983162472 | 1.7117 | 33.6148
605122 | Mubende | Mubende | Camusat | 783909688 | 00983162597 | 0.5653 | 31.3814
605064 | MTN BAT | Kampala | Netis | 771405049 | 01032481814 | 0.31948 | 32.5979
605301 | Mityana Market | Mityana | Camusat | 788160057 | 0108975802 | 0.40136 | 32.0459
605021 | Mbarara Golf | Mbarara | Camusat | 771000158 | 01034467357 | -0.61077 | 30.6584
605247 | Mbale SS | Mbale | Netis | 783909654 | 00983162530 | 1.081 | 34.172
605790 | Masindi | Masindi | Camusat | 772718183 | 01032434243 | 1.6822 | 31.7184
605020 | Masaka Sports | Masaka | Camusat | 771000170 | 01034466227 | -0.33723 | 31.7341
605082 | Luwero | Luwero | Netis | 771405156 | 01032384067 | 0.84119 | 32.4929
605121 | Lira | Lira | I-Engineering | 771003226 | 01034453340 | 2.2355 | 32.9042
605124 | Gulu | Gulu | I-Engineering | 788160066 | 0108975804 | 2.7689 | 32.3021
605101 | Fortportal | Kabarole | Camusat | 783909687 | 00983162589 | 0.64693 | 30.2737
605185 | Colline Hotel | Mukono | Netis | 783909702 | 00983162605 | 0.35804 | 32.7545
Note on B31: Author: From the spares